## Read me
Read Me
1)
Dear User, thank you for using my template. Please remove sample entries from the register
2)
Usually only cells on the sheet "Register" require data-entry. Cells containing formulas or functions are protected, the password is blank should you wish to modify anything.
3)
To avoid typing mistakes resulting in incorrect dashboard results, the entries in some columns are restricted. To modify acceptable values change entries in corresponding tables on the sheet "data validation".
4)
To add an entry to the register click the first free cell in column "Change #" immediately under the last entry and start typing. Alternativly you can mark a cell in the last row and press "Tab" repeatedly until a new line/dataset is added automatically to the table.

## Register
Project Name: |  | [Project Name] | [8 empty] | Last Updated Date: |  | [last updated]
Project Manager: |  | [Project Manager] | [8 empty] | Last Updated by: |  | [updated by]
Change # | Change Description (current situation and desired outcome of change) | Request Date | Requestor | Type of Change Request | Affected Milestone | Cost Impact (USD) | Time Impact (Workdays) | Change Priority | Change Status | Responsible | Target Date | Closing Date | Solution
1 | Scope addition… | 2017-08-01 | Client | Scope | MILE12345 | 10000 | 30 | critical | approved | Peter | 2017-08-02 | 2017-08-03 | Variation order issued to contractor, cost and schedule impact agreed and approved
2 | Scope ommission… | 2017-09-12 | Client | Scope | MILE12346 | -1500 | -3 | medium | under review | Paul | 2017-10-17
3 | Completion of … item is needed 2 days earlier to allow for testing… | 2017-10-15 | QA/QC Mngr. | Schedule | MILE12347 | 1000 | -2 | high | approved | Mary | 2017-10-25 | 2017-10-24 | Change of activity sequence agreed, temp. extra resources to be provided, cost and time impact agreed and approved
Note on D4: MAR : "Requestor" means the individual or organization by whom the change was introduced.
Note on F4: MAR : "Affected Milestone" means the milestone in the milestone list or schedule baseline or approved update thereto.
Note on G4: MAR: Enter the estimated cost impact of this change as posotive or negative value (whatever the case may be).
Note on H4: MAR: Enter the impact in days as positive or negative value. This is usually only neceessary if an item on the critical path is affected.
Note on K4: MAR : "Owner" means the person or organization being assigned responsibility to close the particular request.
Note on L4: MAR : "Target Date" is the date by when a solution should/must be agreed upon. (dd/mm/yyyy)
Note on M4: MAR : "Closing Date" is the date by when a Solution was actually agreed upon. (dd/mm/yyyy)

## Dashboard
Cost Impact (USD) | 9500 | Total No. Changes | 3
Time Impact (Workdays) | 25
open | 0 | Client | 2
under review | 1 | Contractor | 0
approved | 2 | PM | 0
rejected | 0 | QA/QC Mngr. | 1
|  | Sponsor | 0
critical | 1 | Cost | 0
high | 1 | Schedule | 1
medium | 1 | Scope | 2
low | 0

## data validation
Priority | Status | Requestor | Responsible | Change Type
critical | open | Client | Peter | Cost
high | under review | Contractor | Paul | Schedule
medium | approved | PM | Mary | Scope
low | rejected | QA/QC Mngr.
Sponsor