## Read me
Read Me
1)
Dear User, thank you for using my template. Please remove sample entries from the register
2)
A register is designed to be filled with data for ONLY ONE type (grade) of concrete. Consequently you have to use separate registers if you are using different concrete mixes.
3)
Usually only cells on the sheet "Register" require data-entry. Cells containing formulas or functions are protected, the password is blank should you wish to modify anything.
4)
To avoid typing mistakes resulting in incorrect filter results, the entries in the column "Supplier" are restricted. To modify acceptable values change entries on the sheet "Supplier".
5)
To get correct charts, keep controlling that the entire range of data is covered. By default only the entries until line 100 are covered by charts 3 & 4 on the dashboard and only as many entries as existing are covered by chart 5. Chart 5 therefore has to be checked often. For adjustment right click the chart area and choose "Select Data" from the menue. In the "Select Data Source" window one by one update the series by changing the "Series Values" (you may find something like "='Register'!$CC$10:$CC$100", just change the "100" to "200" etc.).
6)
On the sheet "Total QTYs" only enter the start date in the first line of the table. Everything else will update automatically.

## Register
Project: |  | [Project Name] | [8 empty] | Concrete Pouring Register
Sub-Project or Phase: |  | [Sub-Project or Phase]
Client: |  | [Client] | [8 empty] | Project Mngr.: |  |  |  | [Proj. Mngr.] | [5 empty] | Printed on |  |  |  | 2015-03-11
Client's Representative: |  | [Client's Representative] | [8 empty] | QA/QC Mngr.: |  |  |  | [QA/QC Mngr.]
Contractor: |  | [Contractor] | [8 empty] | Mix Design: |  |  |  | [Mix Design]
[11 empty] | Ref.-No.: |  |  |  | [ref.number]
SN | Cube ID |  | No. of Cubes | Delivery Note(s) | Supplier | Concrete Poured on | Grade | QTY (m3) | 7-days test | [5 empty] | 14-days test |  |  |  |  | 28-days test | [6 empty] | Cu Sum | x̄ | Distr.
[9 empty] | Date | Result (N/mm2) |  |  |  | Ø | Date | Result (N/mm2) |  |  | Ø | Date |  | Result (N/mm2) |  |  | Ø | Result
A | B |  | C | D | E | F | G | H | I1 | I2 |  | I3 | I4 | I5 | J1 | J2 | J3 | J4 | J5 | K1 |  | K2 | K3 | K4 | K5 | K6 | L | M | N
1 | B1-BM-GB-A1:A10 - 01/01/2015 |  | 9 | 1234, 1235, 1236 | Supplier A | 2015-01-01 | 37 | 19 | 2015-01-08 | 35.1 |  | 34 | 35.3 | 34.8 | 2015-01-15 | 37.9 | 37.3 | 38.3 | 37.8333 | 2015-01-29 |  | 39.7 | 38.9 | 39.9 | 39.5 | Passed | 2.5 | 39.5 | 0.42436
2 | B2-BM-GB-A1:A10 - 01/01/2015 |  | 9 | 1237, 1238, 1239 | Supplier B | 2015-01-01 | 37 | 19 | 2015-01-08 | 35.3 |  | 34.1 | 35.2 | 34.8667 | 2015-01-15 | 38.1 | 37.4 | 38.2 | 37.9 | 2015-01-29 |  | 39.9 | 39 | 39.8 | 39.5667 | Passed | 2.5667 | 39.5333 | 0.44816
3 | B3-BM-GB-A1:A10 - 01/01/2015 |  | 9 | 1240, 1241, 1242 | Supplier C | 2015-01-01 | 37 | 19 | 2015-01-08 | 37.5 |  | 36.2 | 37.1 | 36.9333 | 2015-01-15 | 40.3 | 39.5 | 40.1 | 39.9667 | 2015-01-29 |  | 42.1 | 40.1 | 41.7 | 41.3 | Passed | 4.3 | 40.1222 | 0.11999
4 | B1-BM-GB-B1:B10 - 01/01/2015 |  | 9 | 1243, 1244, 1245 | Supplier D | 2015-01-01 | 37 | 19 | 2015-01-08 | 35.7 |  | 34.3 | 35 | 35 | 2015-01-15 | 38.5 | 37.6 | 38 | 38.0333 | 2015-01-29 |  | 40.3 | 39.2 | 39.6 | 39.7 | Passed | 2.7 | 40.0167 | 0.4883
5 | B2-BM-GB-B1:B10 - 01/01/2015 |  | 9 | 1246, 1247, 1248 | Supplier E | 2015-01-01 | 37 | 19 | 2015-01-08 | 35.9 |  | 34.4 | 34.9 | 35.0667 | 2015-01-15 | 38.7 | 37.7 | 37.9 | 38.1 | 2015-01-29 |  | 40.5 | 39.3 | 39.5 | 39.7667 | Passed | 2.7667 | 39.9667 | 0.50377
6 | B3-BM-GB-B1:B10 - 01/01/2015 |  | 9 | 1249, 1250, 1251 | Supplier A | 2015-01-01 | 37 | 19 | 2015-01-08 | 35.1 |  | 33.5 | 33.8 | 34.1333 | 2015-01-15 | 37.9 | 36.8 | 36.8 | 37.1667 | 2015-01-29 |  | 39.7 | 38.4 | 38.4 | 38.8333 | Passed | 1.8333 | 39.7778 | 0.16012
7 | B1-BM-GB-C1:C10 - 02/01/2015 |  | 9 | 1252, 1253, 1254 | Supplier B | 2015-01-02 | 37 | 19 | 2015-01-09 | 36.3 |  | 34.6 | 34.7 | 35.2 | 2015-01-16 | 39.1 | 37.9 | 37.7 | 38.2333 | 2015-01-30 |  | 40.9 | 39.5 | 39.3 | 39.9 | Passed | 2.9 | 39.7952 | 0.5238
8 | B2-BM-GB-C1:C10 - 02/01/2015 |  | 9 | 1255, 1256, 1257 | Supplier C | 2015-01-02 | 37 | 19 | 2015-01-09 | 36.5 |  | 34.7 | 34.6 | 35.2667 | 2015-01-16 | 39.3 | 38 | 37.6 | 38.3 | 2015-01-30 |  | 41.1 | 39.6 | 39.2 | 39.9667 | Passed | 2.9667 | 39.8167 | 0.5279
9 | B3-BM-GB-C1:C10 - 02/01/2015 |  | 9 | 1258, 1259, 1260 | Supplier D | 2015-01-02 | 37 | 19 | 2015-01-09 | 36.7 |  | 34.8 | 34.5 | 35.3333 | 2015-01-16 | 39.5 | 38.1 | 37.5 | 38.3667 | 2015-01-30 |  | 41.3 | 39.7 | 39.1 | 40.0333 | Passed | 3.0333 | 39.8407 | 0.5279
10 | B1-BM-SL-A1:C10 - 09/01/2019 |  | 9 | 1261, 1262, 1263 | Supplier E | 2015-01-09 | 37 | 27 | 2015-01-16 | 38.9 |  | 36.9 | 36.4 | 37.4 | 2015-01-23 | 41.7 | 40.2 | 39.4 | 40.4333 | 2015-02-06 |  | 43.5 | 41.8 | 39 | 41.4333 | Passed | 4.4333 | 40 | 0.087159
Note on C7: Marc Arnecke, PMP: Please create a system for the marking of cubes, which allows you to identify cubes and correlate them with portions of your work. A sample is provided on sheet "Cube ID".
Note on N7: Marc Arnecke, PMP: This register is designed for 9 cubes per line only.
Note on AB7: Marc Arnecke, PMP: You may define the suppliers on sheet "Supplier".
Note on AJ7: Marc Arnecke, PMP: Please do not mix different grades in a sheet.

## Dashboard
[ref.number]
Total number of cubes |  |  | 90 | [5 empty] | Total number of cubes | 90
Concrete QTY m3 |  |  | 198 | [5 empty] | Failed | 0
[9 empty] | Passed | 10
Average no. cubes per m3 |  |  |  | 0.45455 |  |  |  |  | Percentage failed |  | 0%
As of |  |  |  | 2015-01-09 |  |  |  |  | As of |  | 2015-02-06
Failed | 0 |  |  |  | As of | 2015-02-06
x̄ | 40 | MPa |  |  | σ | 0.75498 | MPa | As of | 2015-02-06

## Total QTYs
Project: |  | [Project Name] | [5 empty] | Total Concrete QTYs
Sub-Project or Phase: |  | [Sub-Project or Phase]
Client: |  | [Client] | [5 empty] | Project Mngr.: |  | [Proj. Mngr.] |  |  | Printed on |  | 2015-03-11
Client's Repres.: |  | [Client's Representative] | [5 empty] | QA/QC Mngr.: |  | [QA/QC Mngr.]
Contractor: |  | [Contractor] | [5 empty] | Mix Design: |  | [Mix Design]
[8 empty] | Ref.-No.: |  | [ref. no.]
SN | Period |  |  | Consumption |  | Supplier A | Supplier B |  | Supplier C |  | Supplier D | Supplier E |  | Remarks
| Start |  | End | This Period | Cummulative
A | B |  | C | D | E | F | G |  | H |  | I | J |  | K
1 | 2015-01-01 |  | 2015-01-31 | 198 | 198 | 38 | 38 |  | 38 |  | 38 | 46
2 | 2015-02-01 |  | 2015-02-28
3 | 2015-03-01 |  | 2015-03-31
4 | 2015-04-01 |  | 2015-04-30
5 | 2015-05-01 |  | 2015-05-31
6 | 2015-06-01 |  | 2015-06-30
7 | 2015-07-01 |  | 2015-07-31
8 | 2015-08-01 |  | 2015-08-31
9 | 2015-09-01 |  | 2015-09-30
10 | 2015-10-01 |  | 2015-10-31
11 | 2015-11-01 |  | 2015-11-30
12 | 2015-12-01 |  | 2015-12-31
13 | 2016-01-01 |  | 2016-01-31
14 | 2016-02-01 |  | 2016-02-29
15 | 2016-03-01 |  | 2016-03-31
16 | 2016-04-01 |  | 2016-04-30
17 | 2016-05-01 |  | 2016-05-31
18 | 2016-06-01 |  | 2016-06-30
19 | 2016-07-01 |  | 2016-07-31
20 | 2016-08-01 |  | 2016-08-31
21 | 2016-09-01 |  | 2016-09-30
22 | 2016-10-01 |  | 2016-10-31
23 | 2016-11-01 |  | 2016-11-30
24 | 2016-12-01 |  | 2016-12-31
|  |  |  | Total: | 198 | 38 | 38 |  | 38 |  | 38 | 46
Formulas:
End = EDATE([Start],1)-1
Start = EDATE([Start, row above],1)
Note on C10: Marc Arnecke, PMP: Insert start date of your concrete pouring.

## Supplier
Supplier A
Supplier B
Supplier C
Supplier D
Supplier E

## Cube ID
Location |  | Area |  | Item |  | Narration |  | This table technically is without function and just provides a sample how to build a cube ID.
B1 | Building 1 | GN | Site/General | CL | Column | A1:B5 | here Gridline A1 - B5
B2 | Building 2 | BM | Basement | GB | Ground Beam | …
B3 | Building 3 | GF | Groundfloor | IB | Intermediate Beam
GN | General | MF | Mezzanine Floor | SL | Slab
|  | F1 | Floor 1 | WA | Wall
…
|  | F11 | Floor 11
|  | RF | Roof
GN