## Read me
Read Me
1)
Dear User, thank you for using my template. Please remove sample entries from the register
2)
Usually only cells on the sheet "Register" require data-entry. Cells containing formulas or functions are protected, the password is blank should you wish to modify anything.
3)
To avoid typing mistakes resulting in incorrect filter results, some entries in different columns of the register are restricted. To modify acceptable values change entries on the sheet "Validation".

## Register
Project: |  |  | [Project Name] |  |  |  | Inspection & Testing Register
Sub-Project or Phase: |  |  | [Sub-Project or Phase]
Client: |  |  | [Client] |  |  |  | Project Mngr.: |  | [Proj. Mngr.] |  |  |  |  | Printed on |  |  | 2015-03-23
Client's Representative: |  |  | [Client's Representative] |  |  |  | QA/QC Mngr.: |  | [QA/QC Mngr.]
Contractor: |  |  | [Contractor]
[7 empty] | Ref.-No.: |  | [ref.number]
ID | Date | Type of Inspection |  | WBS ID | ITR No. | Ref. Document (Drawing, MS, Spec. etc.) |  | Executor |  | Insp. Phase | Desired Insp. |  | Location | Insp. On | Days | Result |  | Rejection Reason |  |  |  |  | Remarks
[11 empty] | Date | Time | [5 empty] | Material | Method | Machine | Man | Environm.
A | B | C |  | D | E | F |  | G |  | H | I | J | K | L | M | N |  | R | S | T | U | V | W
1 | 2014-08-07 | Material |  | Plaster Sand |  |  |  | Executor A |  | Follow-up | 2014-08-08 | 8:30 | Site Warehouse | 2014-08-08 | 0 | Rejected |  |  |  |  | X
2 | 2014-08-19 | Craftsmanship |  | B2-BM-GB-A1:A10 |  |  |  | Executor A |  | Initial | 2014-08-20 | 14:30 | Location 2 | 2014-09-17 | 28 | Appr. w/c
3 | 2014-08-19 | Craftsmanship |  | B3-BM-GB-A1:A10 |  |  |  | Executor A |  | Final | 2014-08-22 | 10:00 | Location 3 |  |  | Rejected |  |  |  |  | X
4 | 2014-09-01 | Craftsmanship |  | B4-BM-GB-A1:A10 |  |  |  | Executor A |  | Follow-up | 2014-09-02 | 8:30 | Location 4 | 2014-09-02 | 0 | Approved
5 | 2014-09-01 | Craftsmanship |  | B5-BM-GB-A1:A10 |  |  |  | Executor A |  | Initial | 2014-09-02 | 8:30 | Location 5 | 2014-09-02 | 0 | Approved
6 | 2014-09-02 | Craftsmanship |  | B6-BM-GB-A1:A10 |  |  |  | Executor A |  | Final | 2014-09-02 | 10:00 | Location 6 | 2014-09-02 | 0 | Approved
7 | 2014-09-02 | Craftsmanship |  | B7-BM-GB-A1:A10 |  |  |  | Executor A |  | Follow-up | 2014-09-03 | 8:30 | Location 7 | 2014-09-03 | 0 | Approved
8 | 2014-09-03 | Craftsmanship |  | B8-BM-GB-A1:A10 |  |  |  | Executor A |  | Initial | 2014-09-04 | 8:30 | Location 8 | 2014-09-04 | 0 | Approved
9 | 2014-09-04 | Craftsmanship |  | B9-BM-GB-A1:A10 |  |  |  | Executor A |  | Final | 2014-09-05 | 8:30 | Location 9 | 2014-09-05 | 0 | Approved
10 | 2014-09-05 | Craftsmanship |  | B1-BM-GB-A1:A10 |  |  |  | Executor A |  | Follow-up | 2014-09-06 | 8:30 | Off-site | 2014-09-06 | 0 | Approved
11 | 2014-09-06 | Craftsmanship |  | B1-BM-GB-A1:A20 |  |  |  | Executor A |  | Initial | 2014-09-08 | 8:30 | Location 1 | 2014-09-08 | 0 | Appr. w/c
12 | 2014-09-06 | Material |  | Non-shrink Grout |  |  |  | Executor A |  | Final | 2014-09-08 | 7:30 | Site Warehouse | 2014-09-08 | 0 | Appr. w/c
13 | 2014-09-08 | Craftsmanship |  | B1-BM-GB-A1:A22 |  |  |  | Executor A |  | Follow-up | 2014-09-09 | 8:30 | Location 3 | 2014-09-09 | 0 | Rejected | [5 empty] | X
14 | 2014-09-08 | Craftsmanship |  | B1-BM-GB-A1:A23 |  |  |  | Executor A |  | Initial | 2014-09-09 | 8:30 | Location 4 | 2014-09-09 | 0 | Rejected |  | X
15 | 2014-09-08 | Craftsmanship |  | B1-BM-GB-A1:A24 |  |  |  | Executor A |  | Final | 2014-09-09 | 8:30 | Location 5 | 2014-09-09 | 0 | Rejected |  |  |  |  | X
16 | 2014-09-08 | Craftsmanship |  | B1-BM-GB-B1:B10 |  |  |  | Executor A |  | Follow-up | 2014-09-09 | 8:30 | Location 6 | 2014-09-09 | 0 | Approved
17 | 2014-09-08 | Material |  | Cement |  |  |  | Executor A |  | Initial | 2014-09-09 | 9:00 | Site Warehouse | 2014-09-09 | 0 | Approved
18 | 2014-09-09 | Craftsmanship |  | B2-BM-GB-B1:B10 |  |  |  | Executor A |  | Final | 2014-09-10 | 8:30 | Location 8 | 2014-09-10 | 0 | Approved
19 | 2014-09-09 | Craftsmanship |  | B3-BM-GB-B1:B10 |  |  |  | Executor A |  | Follow-up | 2014-09-10 | 8:30 | Location 9 | 2014-09-10 | 0 | Approved
20 | 2014-09-09 | Craftsmanship |  | B1-BM-GB-C1:C10 |  |  |  | Executor A |  | Initial | 2014-09-10 | 8:30 | Off-site | 2014-09-10 | 0 | Approved
21 | 2014-09-10 | Craftsmanship |  | B2-BM-GB-C1:C10 |  |  |  | Executor A |  | Final | 2014-09-11 | 8:30 | Location 1 | 2014-09-11 | 0 | Approved
22 | 2014-09-10 | Craftsmanship |  | B3-BM-GB-C1:C10 |  |  |  | Executor A |  | Follow-up | 2014-09-11 | 8:30 | Location 2 | 2014-09-11 | 0 | Approved
23 | 2014-09-10 | Craftsmanship |  | B1-BM-SL-A1:C10 |  |  |  | Executor A |  | Follow-up | 2014-09-11 | 8:30 | Location 3 | 2014-09-11 | 0 | Approved
24 | 2014-09-10 | Craftsmanship | [5 empty] | Executor A |  | Follow-up | 2014-09-11 | 8:30 | Location 4 | 2014-09-11 | 0 | Approved
25 | 2014-09-11 | Craftsmanship | [5 empty] | Executor A |  | Follow-up | 2014-09-12 | 8:30 | Location 5 | 2014-09-12 | 0 | Approved
26 | 2014-09-11 | Craftsmanship | [5 empty] | Executor A |  | Follow-up | 2014-09-12 | 8:30 | Location 6 | 2014-09-12 | 0 | Approved
27 | 2014-09-11 | Craftsmanship | [5 empty] | Executor A |  | Follow-up | 2014-09-12 | 8:30 | Location 7 | 2014-09-12 | 0 | Approved
28 | 2014-09-11 | Craftsmanship | [5 empty] | Executor A |  | Follow-up | 2014-09-12 | 8:30 | Location 8 | 2014-09-12 | 0 | Approved
29 | 2014-09-12 | Craftsmanship | [5 empty] | Executor A |  | Follow-up | 2014-09-13 | 8:30 | Location 1 | 2014-09-13 | 0 | Approved
30 | 2014-09-12 | Craftsmanship | [5 empty] | Executor A |  | Follow-up | 2014-09-13 | 8:30 | Off-site | 2014-09-13 | 0 | Approved
31 | 2014-09-12 | Craftsmanship | [5 empty] | Executor A |  | Follow-up | 2014-09-13 | 8:30 | Location 1 | 2014-09-13 | 0 | Approved
32 | 2014-09-13 | Craftsmanship | [5 empty] | Executor A |  | Follow-up | 2014-09-15 | 8:30 | Location 2 | 2014-09-15 | 0 | Approved
33 | 2014-09-13 | Material |  | Tiles |  |  |  | Executor A |  | Follow-up | 2014-09-15 | 8:30 | Site Warehouse | 2014-09-15 | 0 | Rejected |  |  |  | X
34 | 2014-09-13 | Craftsmanship | [5 empty] | Executor A |  | Follow-up | 2014-09-15 | 8:30 | Location 4 | 2014-09-15 | 0 | Rejected |  |  | X
35 | 2014-09-15 | Craftsmanship | [5 empty] | Executor A |  | Follow-up | 2014-09-16 | 8:30 | Location 5 | 2014-09-16 | 0 | Appr. w/c
36 | 2014-09-15 | Craftsmanship | [5 empty] | Executor A |  | Follow-up | 2014-09-16 | 8:30 | Location 6
37 | 2014-09-15 | Craftsmanship | [5 empty] | Executor A |  | Follow-up | 2014-09-16 | 8:30 | Location 7
38 | 2014-09-15 | Craftsmanship | [5 empty] | Executor A |  | Follow-up | 2014-09-16 | 8:30 | Location 8
39 | 2014-09-16 | Craftsmanship | [5 empty] | Executor A |  | Follow-up | 2014-09-17 | 8:00 | Location 9
40 | 2014-09-16 | Craftsmanship | [5 empty] | Executor A |  | Follow-up | 2014-09-17 | 8:30 | Off-site

## Dashboard
[ref.number]
Total ITR | 40 |  |  | Material | 1
Approved | 24 |  |  | Method | 1
Appr. w/c | 4 |  |  | Machine | 1
Rejected | 7 |  |  | Man | 3
Pending | 5 |  |  | Environment | 1
Material | 4 |  |  | Initial |  | 7
Craftsmanship | 36 |  |  | Follow-up |  | 26
|  |  |  | Final |  | 7
Location 1 | 4
Location 2 | 3
Location 3 | 3
Location 4 | 4
Location 5 | 4
Location 6 | 4
Location 7 | 3
Location 8 | 4
Site Warehouse | 4
Off-Site | 4
Location 1 | 4 | 0 | 0
Location 2 | 3 | 0 | 0
Location 3 | 3 | 2 | 66.6667
Location 4 | 4 | 2 | 50
Location 5 | 4 | 1 | 25
Location 6 | 4 | 0 | 0
Location 7 | 3 | 0 | 0
Location 8 | 4 | 0 | 0
Site Warehouse | 4 | 2 | 50
Off-Site | 4 | 0 | 0

## Validation
Executor A | Location 1 | Material | Approved
Executor B | Location 2 | Craftsmanship | Appr. w/c
Executor C | Location 3 |  | Rejected
Executor D | Location 4
Location 5
Location 6
Location 7
Location 8
Site Warehouse
Off-Site